## Hoja 1
SPRINT 3 (15 March 2019)
Global map and first battle map
Isometric prespective camera
Enemy Entities base
Characters Entities base
XML templates
UI Start Menu
SPRINT 4 (22 March 2019)
The first character movement
the first enemy movement
Pathfinding system
UI hud and movement
Inputs
SPRINT 5 (05 April 2019)
Enemies AI
New character and attacks
New enemy and attakcs
UI Battle Menu
SPRINT 6 (12 April 2019)
New 2 character
The first ability for the characters
Cut scenes
UI options menu
SPRINT 7 (19 April 2019) | 22 April Vertical Slide
Cut scenes
Do Vertical Slide demostration
Objects if posible
UI win/lose condition and time
SPRINT 8 (03 May 2019)
Cut scenes
New map
New 2 characters
New Enemy
Abilities tree
SPRINT 9 (10 May 2019)
Cut scenes
New map
New 2 characters
Minibosses
SPRINT 10 (17 May 2019) | 19 May Alpha
New map
Final Boss
Special abilities
SPRINT 11 (24 May 2019)
Balance stadistics
BUGFIX
SPIRNT 12 (31 May 2019) | 2 June Gold Versión
BUGFIX