## Hoja 1
SPRINT 1 (Wiki Part 1) 25/2 - 05/3
|  | Estimated Time | Cere Venteo | Gerard Berenguer | Aleix | Guillem | Martí | Ricky | Kevin | Eric | Real Time | Deviation Time
Organization Plan |  | 1 | 2 | 2 | [6 empty] | 4 | 3
Wiki Organization |  | 1 | 3 | [7 empty] | 3 | 2
Welcome Page |  | 2 |  | 1 | [6 empty] | 1 | 1
General Analysis original game |  | 5 |  | 5 | [6 empty] | 5 | 0
Game Design Document |  | 12 |  |  | 9.5 | [5 empty] | 9.5 | 2.5
Tech Design Document |  | 12 | 2 |  |  | 1 |  |  |  | 0.5 | 3.5 | 8.5
User Interface Document |  | 15 |  |  |  |  | 2.5 |  |  | 2.5 | 5 | 10
Art Bible |  | 35 | [6 empty] | 0.8 | 2 | 2.8 | 32.2
QA Plan |  | 13 | [5 empty] | 10 |  |  | 10 | 3
Production Plan |  | 10 |  | 4 | [6 empty] | 4 | 6
Comunity Manager Task |  | 5 | [8 empty] | 0 | 5
| Total Sprint | 111 | 7 | 12 | 9.5 | 1 | 2.5 | 10 | 0.8 | 5 | 47.8 | 73.2
SPRINT 2 (Wiki Part 2) 06/3 - 10/3
|  | Estimated Time | Cere Venteo | Gerard Berenguer | Aleix | Guillem | Martí | Ricky | Kevin | Eric | Real Time | Deviation Time
Organization Plan |  | 2 | 1 | [7 empty] | 1 | 1
Wiki Organization |  | 1 |  | 2 | [6 empty] | 2 | 1
Game Design Document |  | 17 |  |  | 8.5 | [5 empty] | 8.5 | 8.5
Tech Design Document |  | 12 |  |  |  | 1 |  |  |  |  | 1 | 11
User Interface Document |  | 6 |  |  |  |  | 5.5 |  |  | 6 | 11.5 | 5.5
Art Bible |  | 26 | [6 empty] | 21 |  | 21 | 5
Audio Bible |  | 8 | [5 empty] | 2 |  |  | 2 | 6
Manager Control |  | 2 | 1 | 1 | [6 empty] | 2 | 0
Wiki Revision |  | 2 | 1 | 1 |  |  |  | 3.5 |  | 7 | 12.5 | 10.5
Start and Organize Code |  | 8 | 5 | [7 empty] | 9 | 1
STL integration |  | 20 | 7 | [7 empty] | 7 | 13
| Total Sprint | 104 | 15 | 4 | 8.5 | 1 | 5.5 | 5.5 | 21 | 13 | 77.5 | 62.5
SPRINT 3 (VS Part 1) 11/3 - 15/3
|  | Estimated Time | Cere Venteo | Gerard Berenguer | Aleix | Guillem | Martí | Ricky | Kevin | Eric | Real Time | Deviation Time
Earn 100 followers |  | 5 | [8 empty] | 0 | 5
Finish std start code |  | 6 | 4 | [7 empty] | 4 | 2
Refill Excel Concept Part 2 |  | 1 | 0.5 | 1 | [6 empty] | 1.5 | 0.5
Isometric perspective camera |  | 4 | [8 empty] | 0 | 4
Enemies entities Base |  | 4 | 6 | [7 empty] | 6 | 2
Characters entities Base |  | 4 | [8 empty] | 0 | 4
UI Start Menu |  | 6 |  |  |  |  | 4 |  |  | 12 | 16 | 10
Version 0.1 release |  | 1 | [5 empty] | 1 |  |  | 1 | 0
Test and bugs report |  | 6 | [5 empty] | 3.8 |  |  | 3.8 | 2.2
| Total Sprint | 30 | 10.5 | 1 | 0 | 0 | 4 | 4.8 | 0 | 12 | 32.3 | 29.7
SPRINT 4 (VS Part 2) 18/3 - 02/4
|  | Estimated Time | Cere Venteo | Gerard Berenguer | Aleix | Guillem | Martí | Ricky | Kevin | Eric | Real Time | Deviation Time
Excel 0.1 and tasks organization 0.2 |  | 2 | 2 | [7 empty] | 2 | 0
Inputs |  | 4 | 3.5 |  | 5.5 | [5 empty] | 9 | 5
Characters entities base |  | 4 |  |  |  | 3 |  |  |  |  | 3 | 1
Pathfinding system |  | 6 | 4 |  |  | 4 |  |  |  |  | 8 | 2
Iris Movement |  | 6 | 3 |  |  | 4 |  |  |  |  | 7 | 1
Hotdog Movement |  | 6 | 12 | [7 empty] | 12 | 6
UI HUD Battle |  | 10 |  |  |  |  | 7 |  |  | 1 | 8 | 2
UI Main Menu Art |  | 3 | [7 empty] | 3 | 3 | 0
Character Art |  | 12 | [7 empty] | 7.5 | 7.5 | 4.5
First level map |  | 6 |  |  | 1 |  |  |  | 2 |  | 3 | 3
Test and bugs reports |  | 5 | [5 empty] | 1 |  |  | 1 | 4
Version 0.2 release |  | 8 | [5 empty] | 1 |  |  | 1 | 7
|  | 20 | [8 empty] | 0 | 20
| Total Sprint | 92 | 24.5 | 0 | 6.5 | 11 | 7 | 2 | 2 | 11.5 | 64.5 | 55.5
SPRINT 5 (VS Part 3) 03/4 - 10/4
|  | Estimated Time | Cere Venteo | Gerard Berenguer | Aleix | Guillem | Martí | Ricky | Kevin | Eric | Real Time | Deviation Time
Excel 0.2 and tasks organization 0.3 |  | 1 | 2 | [7 empty] | 2 | 1
Turn system |  | 5 | 2 | [7 empty] | 2 | 3
Enemies attack |  | 10 | 12 | [7 empty] | 12 | 2
New enemy Boneyman |  | 4 | 6 | [7 empty] | 6 | 2
New character George B. |  | 8 |  |  |  | 5 |  |  |  |  | 5 | 3
Path with walkeable |  | 4 |  |  |  | 4 |  |  |  |  | 4 | 0
New character Sapphire |  | 10 | 4 | [7 empty] | 4 | 6
New enemy Pinkking |  | 10 | 2 | [7 empty] | 2 | 8
UI character |  | 8 |  |  |  |  | 5 |  |  |  | 5 | 3
Battle menu attack |  | 8 |  |  |  |  | 3 |  |  |  | 3 | 5
XML and relative positions |  | 4 | 4 |  |  |  | 1 |  |  |  | 5 | 1
First level map |  | 6 |  |  | 1 |  |  |  | 2 |  | 3 | 3
Release and bug reports 0.3 |  | 4 | [5 empty] | 2 |  |  | 2 | 2
| Total Sprint | 82 | 32 | 0 | 1 | 9 | 9 | 2 | 2 | 0 | 55 | 39
SPRINT 6 (VS Part 4) 11/4 - 15/4
|  | Estimated Time | Cere Venteo | Gerard Berenguer | Aleix | Guillem | Martí | Ricky | Kevin | Eric | Real Time | Deviation Time
Excel 0.3 and tasks organization 0.4 |  | 2 | 2 | [7 empty] | 2 | 0
Wiki |  | 4 |  |  | 2 | [5 empty] | 2 | 2
Inputs Select |  | 4 | 8 | [7 empty] | 8 | 4
Characters attack |  | 12 | 6 |  |  | 5 |  |  |  |  | 11 | 1
Characters defend |  | 4 | 2 | [7 empty] | 2 | 2
Storm |  | 4 | 5 | [7 empty] | 5 | 1
George B. |  | 6 | 7 | [7 empty] | 7 | 1
Iris |  | 4 | 4 | [7 empty] | 4 | 0
Ability 1 |  | 15 | 13 | [7 empty] | 13 | 2
Inputs Gamepad |  | 2 | 1 | [7 empty] | 1 | 1
Path with type movements |  | 8 |  |  |  | 6 |  |  |  |  | 6 | 2
Search attack area |  | 8 |  |  |  | 6 |  |  |  |  | 6 | 2
George B. Spritesheet |  | 10 | [7 empty] | 10 | 10 | 0
Test and Bugs Reports |  | 8 | [5 empty] | 2 |  |  | 2 | 6
Version 0.4 Release |  | 1 | [5 empty] | 1 |  |  | 1 | 0
| Total Sprint | 92 | 48 | 0 | 2 | 17 | 0 | 3 | 0 | 10 | 80 | 24
SPRINT 7 (VS Part 5) 17/4 - 20/4
|  | Estimated Time | Cere Venteo | Gerard Berenguer | Aleix | Guillem | Martí | Ricky | Kevin | Eric | Real Time | Deviation Time
Excel 0.4 and task organization 0.5 |  | 2 | 2 | [7 empty] | 2 | 0
Balance Stats |  | 20 |  |  | 12 | 7 |  |  |  |  | 19 | 1
Bear trap ability |  | 6 | 6 | [7 empty] | 6 | 0
Storm ability |  | 2 | 2 | [7 empty] | 2 | 0
Enemies AI |  | 6 |  |  |  | 3 |  |  |  |  | 3 | 3
Lifebar enemies |  | 1 |  |  |  |  | 2 |  |  |  | 2 | 1
Menu Options in battle UI |  | 8 |  |  |  |  | 6 |  |  |  | 6 | 2
Abilities names UI |  | 1 |  |  |  |  | 1 |  |  |  | 1 | 0
Character UI |  | 2 |  |  |  |  | 2 |  |  |  | 2 | 0
Stun and defend Icons UI |  | 1 |  |  |  |  | 1 |  |  |  | 1 | 0
Numbers UI |  | 1 |  |  |  |  | 1.5 |  |  |  | 1.5 | 0.5
Level 1 map Art |  | 6 | [7 empty] | 25 | 25 | 19
Sapphire Spritesheet |  | 14 | [6 empty] | 10 |  | 10 | 4
Boneyman Spritesheet |  | 10 | [6 empty] | 6 |  | 6 | 4
Pinkking Spritesheet |  | 14 | [7 empty] | 8 | 8 | 6
Bugfixs |  | 20 | 32 |  |  | 14 |  |  |  |  | 46 | 26
Polish |  | 20 | 2 |  |  | 4 |  |  |  |  | 6 | 14
Test and Bugs Reports |  | 40 | 4 |  | 4 | 4 |  | 4 |  |  | 16 | 24
Version 0.5 Release |  | 1 | [5 empty] | 1 |  |  | 1 | 0
| Total Sprint | 175 | 48 | 0 | 16 | 32 | 13.5 | 5 | 16 | 33 | 163.5 | 104.5
SPRINT 8 (Alpha Part 1) 26/4 - 30/4
|  | Estimated Time | Cere Venteo | Gerard Berenguer | Aleix | Guillem | Martí | Ricky | Kevin | Eric | Real Time | Deviation Time
Excel 0.5 and task organization 0.6 |  | 2 | 2 | [7 empty] | 2 | 0
Scene Manager |  | 20 | 14 | [7 empty] | 14 | 6
Transitions |  | 6 | 8 | [7 empty] | 8 | 2
Hektor Character |  | 8 | 1 | [7 empty] | 1 | 7
Language class |  | 2 | 2 |  | 0.5 | [5 empty] | 2.5 | 0.5
Bugfixs |  | 6 | 2 | [7 empty] | 2 | 4
Polish |  | 10 | 8 | [7 empty] | 8 | 2
Test and Bugs Reports |  | 8 | 1 |  |  |  |  | 2 |  |  | 3 | 5
Version 0.6 Release |  | 1 | [5 empty] | 0.5 |  |  | 0.5 | 0.5
| Total Sprint | 63 | 38 | 0 | 0.5 | 0 | 0 | 2.5 | 0 | 0 | 41 | 27
SPRINT 9 (Alpha Part 2) 01/5 - 11/5
|  | Estimated Time | Cere Venteo | Gerard Berenguer | Aleix | Guillem | Martí | Ricky | Kevin | Eric | Real Time | Deviation Time
Excel 0.6 and task organization 0.7 |  | 2 | 2 | [7 empty] | 2 | 0
Battle 2 |  | 4 | 6 | [7 empty] | 6 | 2
Battle 3 |  | 6 | 6 | [7 empty] | 6 | 0
Critic Stat Character |  | 2 | 3 | [7 empty] | 3 | 1
Comeback Action Character |  | 2 | 2 | [7 empty] | 2 | 0
Level Characters |  | 20 | 10 | [7 empty] | 10 | 10
Level 2 Map |  | 20 | [8 empty] | 0 | 20
Level 3 Map |  | 20 | [8 empty] | 0 | 20
Global Map Scene |  | 10 |  |  |  |  | 6 |  |  |  | 6 | 4
Inputs Personalized |  | 4 |  |  | 8 | [5 empty] | 8 | 4
Test and Bugs Reports |  | 4 | [5 empty] | 2.5 |  |  | 2.5 | 1.5
Version 0.7 Release |  | 1 | [5 empty] | 1 |  |  | 1 | 0
| Total Sprint | 95 | 29 | 0 | 8 | 0 | 6 | 3.5 | 0 | 0 | 46.5 | 62.5
SPRINT 10 (Alpha Part 3) 12/5 - 23/5
|  | Estimated Time | Cere Venteo | Gerard Berenguer | Aleix | Guillem | Martí | Ricky | Kevin | Eric | Real Time | Deviation Time
Excel 0.7 and task organization 0.8 |  | 2 | 2 | [7 empty] | 2 | 0
All Characters Abilities |  | 20 | 20 | [7 empty] | 20 | 0
Burgdog Enemy |  | 2 |  |  |  | 1 |  |  |  |  | 1 | 1
Hotdog Enemy |  | 8 |  |  |  | 5 |  |  |  |  | 5 | 3
Better AI |  | 20 |  |  |  | 15 |  |  |  |  | 15 | 5
Polarbear Enemy |  | 2 |  |  |  | 1 |  |  |  |  | 1 | 1
Polarpath Enemy |  | 8 |  |  |  | 3 |  |  |  |  | 3 | 5
Particle System |  | 10 | 2 | [7 empty] | 2 | 8
Test and Bugs Reports |  | 1 | [5 empty] | 1 |  |  | 1 | 0
Version 0.7 Release |  | 1 | [5 empty] | 1 |  |  | 1 | 0
| Total Sprint | 74 | 24 | 0 | 0 | 25 | 0 | 2 | 0 | 0 | 51 | 23
SPRINT 11 (Gold Part 1) 24/5 - 3/6
|  | Estimated Time | Cere Venteo | Gerard Berenguer | Aleix | Guillem | Martí | Ricky | Kevin | Eric | Real Time | Deviation Time
Excel 0.8 and task organization 0.9 |  | 2 | 2 | [7 empty] | 2 | 0
Object Atlas |  | 2 | 2 | [7 empty] | 2 | 0
Defend and Critic Recolor |  | 2 | 4 | [7 empty] | 4 | 2
FX Characters |  | 4 | 4 | [7 empty] | 4 | 0
Debug Buttons |  | 4 | 2 | [7 empty] | 2 | 2
Alpha color Entities |  | 6 | 8 | [7 empty] | 8 | 2
Load and Save |  | 4 | 3 | [7 empty] | 3 | 1
Tutorial |  | 10 |  |  |  | 7 |  |  |  |  | 7 | 3
Intro and Ending Scenes |  | 4 |  |  |  |  | 7 |  |  |  | 7 | 3
Particle Atlas |  | 2 | [8 empty] | 0 | 2
Level 4 Map |  | 20 | [8 empty] | 0 | 20
Storm Spritesheet |  | 14 | [8 empty] | 0 | 14
Burgdog Spritesheet |  | 14 | [8 empty] | 0 | 14
Hotdog Spritesheet |  | 14 | [8 empty] | 0 | 14
Polarbear Spritesheet |  | 14 | [8 empty] | 0 | 14
Polarpath Spritesheet |  | 14 | [8 empty] | 0 | 14
Polish |  | 15 | 20 | [7 empty] | 20 | 5
Test and Bugs Reports |  | 2 | [5 empty] | 3 |  |  | 3 | 1
Version 0.7 Release |  | 1 | [5 empty] | 1 |  |  | 1 | 0
| Total Sprint | 148 | 45 | 0 | 0 | 7 | 7 | 4 | 0 | 0 | 63 | 111
SPRINT 12 (Gold Part 2) 4/6 - 11/6
|  | Estimated Time | Cere Venteo | Gerard Berenguer | Aleix | Guillem | Martí | Ricky | Kevin | Eric | Real Time | Deviation Time
Excel 0.9 and 1.0 and task organization 1.0 |  | 4 | 3 | [7 empty] | 3 | 1
Add Particles |  | 15 | 20 | [7 empty] | 20 | 5
Video with Logo |  | 10 |  |  |  | 5 |  |  |  |  | 5 | 5
Target Info |  | 10 | 8 | [7 empty] | 8 | 2
Abilities Info |  | 10 |  |  |  |  | 8 |  |  |  | 8 | 2
UI Polish |  | 10 |  |  |  |  | 8 |  |  |  | 8 | 2
Portraits Enemies |  | 4 | 2 | [7 empty] | 2 | 2
Recording Attacks Effect |  | 6 | 1 |  | 1 | 1 |  | 1 |  | 1 | 5 | 1
Website |  | 4 |  |  | 3 | [5 empty] | 3 | 1
Readme |  | 4 |  |  | 3 | [5 empty] | 3 | 1
Polish |  | 30 | 25 |  |  | 20 |  |  |  |  | 45 | 15
Presentation |  | 6 | [5 empty] | 4 |  | 4 | 8 | 2
Prepare Outside Testing |  | 4 | [5 empty] | 3 |  |  | 3 | 1
Outside Testing |  | 5 | [5 empty] | 5 |  |  | 5 | 0
Test and Bugs Reports |  | 4 | [5 empty] | 8 |  |  | 8 | 4
Version 0.7 Release |  | 1 | [5 empty] | 1 |  |  | 1 | 0
| Total Sprint | 127 | 59 | 0 | 7 | 26 | 16 | 22 | 0 | 5 | 135 | 44
| Total Tasks | Estimated Time | Cere Venteo | Gerard Berenguer | Aleix | Guillem | Martí | Ricky | Kevin | Eric | Real Time | Deviation Time | Average Deviation ny Task
TOTAL | 156 | 1193 | 380 | 17 | 59 | 129 | 70.5 | 66.3 | 41.8 | 89.5 | 857.1 | 655.9 | 4.2045
Developer | Tasks | Estimated Time | Real Time | Deviation Time | Average Deviation by Task
Cere Venteo | 69 | 508 | 381 | 127 | 7.3623
Gerard Berenguer | 8 | 24 | 17 | 7 | 3
Aleix | 15 | 143 | 59 | 84 | 9.5333
Guillem | 25 | 286 | 129 | 157 | 11.44
Martí | 18 | 111 | 70.5 | 40.5 | 6.1667
Ricky | 26 | 142 | 66.3 | 75.7 | 5.4615
Kevin | 10 | 153 | 41.8 | 111.2 | 15.3
Eric | 19 | 219 | 89.5 | 129.5 | 11.5263